## Timeline
Task \ Week	10	March 9: Final Game Proposal	11	March 16: Physical Prototype & Prototype Chapter	12	13	March 31: First Playable Demo	14	15	16	April 20: Interim Report	17	18	May 4: Alpha Release	19	May 11: Playtesting Results	20	21	May 26: Final Public Presentation
1	A
2			A
3					E
4					MP & MR
5					MT
6						A
7								MP & MR
8			MT*						MT**			MT***								*: first 3, **: 4/5, ***: rest
9								MT*		MT**			MT***
10									MT			MT
11						E		E
12									MP & MR			MP & MR
13										E
14										A
15												E
16													MP & MR
17													A
18															MP & MR
19															A
20																	MP & MR
21																	E & MT
22																		A

## Task List
Task	Description	Who	hrs	actual
1	Finalize game proposal	All
2	Prepare & play physical prototype, prepare report & presentation	All
3	Adjust gameplay balancing using results of physical prototyping	Elias
4	Implement first playable demo (= Functional Minimum)	Marcel & Marco
5	Base creature mesh & simple animations (walk, jump, hit)	Miriam	∞
6	Prepare demo presentation	All
7	Implement 1. evolution phase and extendable framework for cards	Marcel & Marco
8	2D creature card art	Miriam	2/card
9	3D effects of creature cards	Miriam	5/card
10	Attack animations as needed (when implemented in code)	Miriam	∞
11	Design combat mechanics of each card in detail (stats, attacks, balancing)	Elias
12	Implement combat mechanics of each card	Marcel & Marco
13	Level design (arenas)	Elias
14	Prepare interim report	All
15	Sounds & music	Elias
16	Control & Interfaces	Marcel & Marco
17	Prepare alpha presentation	All
18	Networking code for split screen (high target, only if time enough)	Marcel & Marco
19	Playtesting	All
20	Bugfixing	Marcel & Marco
21	Trailer	Elias & Miriam
22	Prepare final presentation	All